## Costos Proyecto
| Horas programadores | Horas extra programadores | Horas managers | Horas extras Managers | Costo programadores | Costo managers | Costo | Costo No Facturable | Costo Acumulado | Cliente | Margen | Porcentaje
2015-03-08 | 96 | 0 | 12 | 0 | $4,800 | $1,200 | $6,000 | 0 | $6,000 | $12,000 | $6,000 | 50.00%
2015-10-08 | 96 | 0 | 12 | 0 | $4,800 | $1,200 | $6,000 | 0 | $12,000 | $24,000 | $12,000 | 50.00%
17/8/2015 | 0 | 0 | 0 | 0 | Feriado | Feriado | 0 | 0 | $12,000 | $24,000 | $12,000 | 50.00%
24/8/2015 | 96 | 0 | 12 | 0 | $4,800 | $1,200 | $6,000 | 0 | $18,000 | $36,000 | $18,000 | 50.00%
31/8/2015 | 96 | 0 | 12 | 0 | $4,800 | $1,200 | $6,000 | 0 | $24,000 | $48,000 | $24,000 | 50.00%
2015-07-09 | 96 | 0 | 12 | 3 | $4,800 | $1,800 | $6,600 | 0 | $30,600 | $61,200 | $30,600 | 50.00%
14/9/2015 | 96 | 0 | 12 | 3 | $4,800 | $1,800 | $6,600 | 0 | $37,200 | $74,400 | $37,200 | 50.00%
21/9/2015 | 96 | 0 | 12 | 3 | $4,800 | $1,800 | $6,600 | 0 | $43,800 | $87,600 | $43,800 | 50.00%
28/9/2016 | 96 | 0 | 12 | 3 | $4,800 | $1,800 | $6,600 | 0 | $50,400 | $100,800 | $50,400 | 50.00%
2015-05-10 | 96 | 11 | 12 | 9 | $5,900 | $3,000 | $8,900 | 0 | $59,300 | $118,600 | $59,300 | 50.00%
2015-12-10 | 0 | 0 | 0 | 0 | Feriado | Feriado | 0 | 0 | $59,300 | $118,600 | $59,300 | 50.00%
19/10/2015 | 96 | 18 | 12 | 3 | $4,800 | $1,800 | $6,600 | $1,800 | $67,700 | $128,200 | $60,500 | 47.19%
26/10/2018 | 96 | 0 | 12 | 4 | $4,800 | $1,800 | $6,600 | 200 | $74,500 | $141,000 | $66,500 | 47.16%
2015-02-11 | 96 | 0 | 12 | 3 | $4,800 | $1,800 | $6,600 | 0 | $81,100 | $154,200 | $73,100 | 47.41%
2015-09-11 | 96 | 0 | 12 | 2 | $4,800 | $1,600 | $6,400 | 0 | $87,500 | $167,000 | $79,500 | 47.60%
Línea de base 4 | [8 empty] | $87,500 | $167,000 | $79,500 | 47.60%
16/11/2019 | 96 | 0 | 12 | 0 | $4,800 | $1,200 | $6,000 |  | $93,500 | $179,000 | $85,500 | 47.77%
TOTAL | 1,248 | 29 | 156 | 33 | $63,500 | $22,000 | $91,500 | $2,000 | $93,500 | $179,000 | $85,500 | 47.77%
| $/hora | $/horas extras | cantidad
Developers: | 50 | 100 | 16
Managers: | 100 | 200 | 4
Horas dev por clase | 6
Horas man. | 3

## Horas
Miembros del Equipo | Rate |  | 3/8/2015 |  | 10/8/2015 |  | 17/8/2015 |  | 24/8/2015 |  | 31/8/2015 |  | 7/9/2015 |  | 14/9/2015 |  | 21/9/2015 |  | 28/9/2016 |  | 5/10/2015 |  | 19/10/2015 |  | 26/10/2018 |  | 2/11/2015 |  | 9/11/2015
Team Number | Hourly Rate | Extra Hour Rate | hours | extra hours | hours | extra hours | hours | extra hours | hours | extra hours | hours | extra hours | hours | extra hours | hours | extra hours | hours | extra hours | hours | extra hours | hours | extra hours | hours | extra hours | hours | extra hours | hours | extra hours | hours | extra hours
1 | 50 | 100 | 6 |  | 6 |  | 0 | 0 | 6 | 0 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 | 2 | 6 | 0 | 6 | 0 | 6 |  | 6
2 | 50 | 100 | 6 |  | 6 |  | 0 | 0 | 6 | 0 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 | 1 | 6 | 2 | 6 | 0 | 6 |  | 6
3 | 50 | 100 | 6 |  | 6 |  | 0 | 0 | 6 | 0 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 | 0 | 6 | 3 | 6 | 0 | 6 |  | 6
4 | 50 | 100 | 6 |  | 6 |  | 0 | 0 | 6 | 0 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 | 3 | 6 | 1 | 6 | 0 | 6 |  | 6
5 | 50 | 100 | 6 |  | 6 |  | 0 | 0 | 6 | 0 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 | 0 | 6 | 2 | 6 | 0 | 6 |  | 6
6 | 50 | 100 | 6 |  | 6 |  | 0 | 0 | 6 | 0 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 | 0 | 6 | 1 | 6 | 0 | 6 |  | 6
7 | 50 | 100 | 6 |  | 6 |  | 0 | 0 | 6 | 0 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 | 2 | 6 | 0 | 6 | 0 | 6 |  | 6
8 | 50 | 100 | 6 |  | 6 |  | 0 | 0 | 6 | 0 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 | 1 | 6 | 2 | 6 | 0 | 6 |  | 6
9 | 50 | 100 | 6 |  | 6 |  | 0 | 0 | 6 | 0 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 | 0 | 6 | 1 | 6 | 0 | 6 |  | 6
10 | 50 | 100 | 6 |  | 6 |  | 0 | 0 | 6 | 0 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 | 2 | 6 | 2 | 6 | 0 | 6 |  | 6
11 | 50 | 100 | 6 |  | 6 |  | 0 | 0 | 6 | 0 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 | 0 | 6 | 0 | 6 | 0 | 6 |  | 6
12 | 50 | 100 | 6 |  | 6 |  | 0 | 0 | 6 | 0 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 | 1 | 6 | 1 | 6 | 0 | 6 |  | 6
13 | 50 | 100 | 6 |  | 6 |  | 0 | 0 | 6 | 0 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 | 1 | 6 | 0 | 6 | 0 | 6 |  | 6
14 | 50 | 100 | 6 |  | 6 |  | 0 | 0 | 6 | 0 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 | 0 | 6 | 2 | 6 | 0 | 6 |  | 6
15 | 50 | 100 | 6 |  | 6 |  | 0 | 0 | 6 | 0 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 | 2 | 6 | 0 | 6 | 0 | 6 |  | 6
16 | 50 | 100 | 6 |  | 6 |  | 0 | 0 | 6 | 0 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 | 0 | 6 | 1 | 6 | 0 | 6 |  | 6
Bucca, Joaquin | 100 | 200 | 3 |  | 3 | 2 | 0 | 0 | 3 | 0 | 3 | 3 | 3 | 2 | 3 |  | 3 | 1 | 3 | 1 | 3 | 3 | 3 | 1 | 3 | 2 | 3 |  | 3
Gutierrez, Martin | 100 | 200 | 3 |  | 3 | 2 | 0 | 0 | 3 | 0 | 3 | 3 | 3 | 3 | 3 | 1 | 3 | 1 | 3 | 1 | 3 | 2 | 3 | 0 | 3 | 1 | 3 |  | 3
Isoldi, Javier | 100 | 200 | 3 | 3 | 3 | 2 | 0 | 0 | 3 | 0 | 3 | 3 | 3 | 3 | 3 | 1 | 3 | 1 | 3 | 1 | 3 | 2 | 3 | 0 | 3 | 0 | 3 |  | 3
Najún Zamora, Tomas | 100 | 200 | 3 |  | 3 | 2 | 0 | 0 | 3 | 0 | 3 | 3 | 3 | 2 | 3 | 1 | 3 |  | 3 |  | 3 | 2 | 3 | 0 | 3 | 0 | 3 |  | 3
SubTotal |  |  | $6,000.00 | $600.00 | $6,000.00 | $1,600.00 | $0.00 | $0.00 | $6,000.00 | $0.00 | $6,000.00 | $2,400.00 | $6,000.00 | $2,000.00 | $6,000.00 | $600.00 | $6,000.00 | $600.00 | $6,000.00 | $600.00 | $6,000.00 | $3,300.00 | $6,000.00 | $2,000.00 | $6,000.00 | $600.00 | $6,000.00 | $0.00 | $6,000.00 | $0.00
Costo Total |  |  | $6,600.00 |  | $7,600.00 |  | $0.00 |  | $6,000.00 |  | $8,400.00 |  | $8,000.00 |  | $6,600.00 |  | $6,600.00 |  | $6,600.00 |  | $9,300.00 |  | $8,000.00 |  | $6,600.00 |  | $6,000.00 |  | $6,000.00
Acumulado |  |  | $6,600.00 |  | $14,200.00 |  | $14,200.00 |  | $20,200.00 |  | $28,600.00 |  | $36,600.00 |  | $43,200.00 |  | $49,800.00 |  | $56,400.00 |  | $65,700.00 |  | $73,700.00 |  | $80,300.00 |  | $86,300.00 |  | $92,300.00
Desvío |  |  | $600.00 |  | $1,600.00 |  | $0.00 |  | $0.00 |  | $2,400.00 |  | $1,400.00 |  | $0.00 |  | $0.00 |  | $0.00 |  | $400.00 |  | $1,400.00 |  | $600.00 |  | $0.00 |  | $0.00
Desvío Total |  |  | $600.00 |  | $2,200.00 |  | $2,200.00 |  | $2,200.00 |  | $4,600.00 |  | $6,000.00 |  | $6,000.00 |  | $6,000.00 |  | $6,000.00 |  | $6,400.00 |  | $7,800.00 |  | $8,400.00 |  | $8,400.00 |  | $8,400.00
% de Desvío |  |  | 0.66% |  | 2.40% |  | 2.40% |  | 2.40% |  | 5.03% |  | 6.56% |  | 6.56% |  | 6.56% |  | 6.56% |  | 6.99% |  | 8.52% |  | 9.18% |  | 9.18% |  | 9.18%

## Costos Estimados UserStories
Id | Descripción | Horas programadores | User Story Points | Retrabajo programadores | Horas managers | Costo programadores | Costo retrabajo | Costo managers | Costo | Costo Acumulado | Costo proporcional a los USP |  |  |  | 21/9/2015 |  | 28/9/2016 |  | 5/10/2015 |  | 19/10/2015 |  | 26/10/2018 |  | 2/11/2015 |  | 9/11/2015 |  | 16/11/2019
[15 empty] | Porcentaje | Terminada | Porcentaje | Terminada | Porcentaje | Terminada | Porcentaje | Terminada | Porcentaje | Terminada | Porcentaje | Terminada | Porcentaje | Terminada | Porcentaje | Terminada
TS-00 | Capacitación | 288 | 50 | 0 | 18 | $14,400.00 | $0.00 | $1,800.00 | $16,200.00 | $16,200.00 | $21,446.08 |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
TS-01 | Loguearse y desloguarse | 24 | 8 | 4 | 6 | $1,200.00 | $200.00 | $600.00 | $2,000.00 | $18,200.00 | $3,431.37 |  |  |  | 0.7 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
TS-02 | Registrarse y cerrar cuenta | 24 | 8 | 4 | 6 | $1,200.00 | $200.00 | $600.00 | $2,000.00 | $20,200.00 | $3,431.37 |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
TS-03 | Recuperar contraseña | 18 | 6 | 3 | 5 | $900.00 | $150.00 | $500.00 | $1,550.00 | $21,750.00 | $2,573.53 |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
TS-04 | Pagar suscripcion | 18 | 6 | 3 | 5 | $900.00 | $150.00 | $500.00 | $1,550.00 | $23,300.00 | $2,573.53 |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
TS-08 | Contratar clase | 18 | 6 | 3 | 5 | $900.00 | $150.00 | $500.00 | $1,550.00 | $24,850.00 | $2,573.53 |  |  |  | 0 | 0 | 0.7 | 0 | 0.7 | 0 | 0.7 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
TS-19 | Contacto | 18 | 6 | 3 | 5 | $900.00 | $150.00 | $500.00 | $1,550.00 | $26,400.00 | $2,573.53 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
TS-05 | Editar perfil alumno | 24 | 8 | 4 | 6 | $1,200.00 | $200.00 | $600.00 | $2,000.00 | $28,400.00 | $3,431.37 |  |  |  | 0.5 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
TS-06 | Editar perfil profesor | 24 | 8 | 4 | 6 | $1,200.00 | $200.00 | $600.00 | $2,000.00 | $30,400.00 | $3,431.37 |  |  |  | 0.5 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
TS-07 | Buscar profesor | 24 | 8 | 4 | 6 | $1,200.00 | $200.00 | $600.00 | $2,000.00 | $32,400.00 | $3,431.37 |  |  |  | 0 | 0 | 0.6 | 0 | 0.6 | 0 | 0.6 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
TS-22 | Cargar materias de profesor | 18 | 6 | 3 | 5 | $900.00 | $150.00 | $500.00 | $1,550.00 | $33,950.00 | $2,573.53 |  |  |  | 0 | 0 | 0.4 | 0 | 0.8 | 0 | 0.8 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
TS-23 | Cargar domicilio profesor | 24 | 8 | 4 | 6 | $1,200.00 | $200.00 | $600.00 | $2,000.00 | $35,950.00 | $3,431.37 |  |  |  | 0 | 0 | 0 | 0 | 0.2 | 0 | 0.7 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0.2 | 0
TS-09 | Aceptar clase | 12 | 4 | 2 | 4 | $600.00 | $100.00 | $400.00 | $1,100.00 | $37,050.00 | $1,715.69 |  |  |  | 0 | 0 | 0 | 0 | 0.8 | 0 | 0.9 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
TS-10 | Calendario profesor | 48 | 18 | 8 | 10 | $2,400.00 | $400.00 | $1,000.00 | $3,800.00 | $40,850.00 | $7,720.59 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0 | 0.4 | 0 | 0 | 0 | 0 | 0
TS-11 | Calendario alumno | 48 | 18 | 8 | 10 | $2,400.00 | $400.00 | $1,000.00 | $3,800.00 | $44,650.00 | $7,720.59 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3 | 0 | 0 | 0 | 0 | 0
TS-16 | Dashboard profesor | 36 | 12 | 6 | 8 | $1,800.00 | $300.00 | $800.00 | $2,900.00 | $47,550.00 | $5,147.06 |  |  |  | 0 | 0 | 0.2 | 0 | 0.5 | 0 | 0.6 | 0 | 1 | 1 | 1 | 1 | 0.5 | 0 | 0.5 | 0
TS-17 | Dashboard alumno | 36 | 12 | 6 | 8 | $1,800.00 | $300.00 | $800.00 | $2,900.00 | $50,450.00 | $5,147.06 |  |  |  | 0 | 0 | 0 | 0 | 0.2 | 0 | 0.5 | 0 | 1 | 1 | 1 | 1 | 0.2 | 0 | 0.2 | 0
TS-12 | Calificar alumnos | 18 | 6 | 3 | 5 | $900.00 | $150.00 | $500.00 | $1,550.00 | $52,000.00 | $2,573.53 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.7 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
TS-18 | Pagina promocional | 18 | 6 | 3 | 5 | $900.00 | $150.00 | $500.00 | $1,550.00 | $53,550.00 | $2,573.53 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.6 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
TS-20 | Login redes sociales | 48 | 18 | 8 | 10 | $2,400.00 | $400.00 | $1,000.00 | $3,800.00 | $57,350.00 | $7,720.59 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0 | 0.3 | 0 | 0 | 0 | 0 | 0
TS-21 | Compartir redes sociales | 48 | 18 | 8 | 10 | $2,400.00 | $400.00 | $1,000.00 | $3,800.00 | $61,150.00 | $7,720.59 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3 | 0 | 0 | 0 | 0 | 0
TS-13 | Servicio de recomendaciones | 36 | 12 | 6 | 8 | $1,800.00 | $300.00 | $800.00 | $2,900.00 | $64,050.00 | $5,147.06 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0 | 0.1 | 0 | 0 | 0 | 0 | 0
TS-14 | Servicio de mensajeria | 60 | 24 | 10 | 10 | $3,000.00 | $500.00 | $1,000.00 | $4,500.00 | $68,550.00 | $10,294.12 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0 | 0.1 | 0 | 0 | 0 | 0 | 0
TS-15 | Reaccionar al termino de periodo de prueba | 36 | 12 | 6 | 8 | $1,800.00 | $300.00 | $800.00 | $2,900.00 | $71,450.00 | $5,147.06 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0 | 0.15 | 0 | 0 | 0 | 0 | 0
[14 empty] | Burned USP | 70 |  | 94 |  | 94 |  | 100 |  | 160 |  | 168 |  | 144 |  | 136
| Total | 738 | 204 | 75 | 129 | [5 empty] | $87,500 |  |  | Ideal Burndown | 134 |  | 114.8571429 |  | 95.71428571 |  | 76.57142857 |  | 57.42857143 |  | 38.28571429 |  | 19.14285714 |  | 0
[14 empty] | Actual Burndown | 134 |  | 110 |  | 110 |  | 104 |  | 44 |  | 36
[14 empty] | Valor ganado | $35,857.84 |  | $46,237.75 |  | $51,899.51 |  | $61,764.71 |  | $73,774.51 |  | $84,411.76
[14 empty] | Costo planeado | $37,200 |  | $43,800 |  | $50,400 |  | $59,300 |  | $67,700 |  | $74,500
[14 empty] | Costo real | $43,200.00 |  | $49,800.00 |  | $56,400.00 |  | $65,700.00 |  | $73,700.00 |  | $80,300.00
[14 empty] | Cost Variance | -$7,342.16 |  | -$3,562.25 |  | -$4,500.49 |  | -$3,935.29 |  | $74.51 |  | $4,111.76
[14 empty] | Schedule Variance | -$1,342.16 |  | $2,437.75 |  | $1,499.51 |  | $2,464.71 |  | $6,074.51 |  | $9,911.76
[14 empty] | C. Performance Indicator | 0.8300426652 |  | 0.9284687771 |  | 0.9202040745 |  | 0.9401020682 |  | 1.001010988 |  | 1.05120504
[14 empty] | S. Performance Indicator | 0.9639205144 |  | 1.055656281 |  | 1.029752179 |  | 1.041563337 |  | 1.08972688 |  | 1.133043822
$/hora.par
[12 empty] | Developers: | 50 | Estimated at completion (EAC = AC + BAC - EV) | $94,842.16 |  | $91,062.25 |  | $92,000.49 |  | $91,435.29 |  | $87,425.49 |  | $83,388.24
[12 empty] | Managers: | 100 | Estimated at completion (EAC = AC + ETC) | $86,450.00
[12 empty] | Cantidad de dias | 7
[12 empty] | Cantidad inicial de USP | 134
[12 empty] | Decremento | 19.14285714

## Costos UserStories
Id | Descripción | Horas programadores | Horas managers | Costo programadores | Costo managers | Costo | Costo Acumulado
TS-00 | Capacitación | 288 | 18 | $14,400.00 | $1,800.00 | $16,200.00 | $16,200.00
TS-01 | Loguearse y desloguarse |  |  | $0.00 | $0.00 | $0.00 | $16,200.00
TS-02 | Registrarse y cerrar cuenta |  |  | $0.00 | $0.00 | $0.00 | $16,200.00
TS-03 | Recuperar contraseña |  |  | $0.00 | $0.00 | $0.00 | $16,200.00
TS-04 | Pagar suscripcion |  |  | $0.00 | $0.00 | $0.00 | $16,200.00
TS-08 | Contratar clase |  |  | $0.00 | $0.00 | $0.00 | $16,200.00
TS-19 | Contacto |  |  | $0.00 | $0.00 | $0.00 | $16,200.00
TS-05 | Editar perfil alumno |  |  | $0.00 | $0.00 | $0.00 | $16,200.00
TS-06 | Editar perfil profesor |  |  | $0.00 | $0.00 | $0.00 | $16,200.00
TS-07 | Buscar profesor |  |  | $0.00 | $0.00 | $0.00 | $16,200.00
TS-22 | Cargar materias de profesor |  |  | $0.00 | $0.00 | $0.00 | $16,200.00
TS-23 | Cargar domicilio profesor |  |  | $0.00 | $0.00 | $0.00 | $16,200.00
TS-09 | Aceptar clase |  |  | $0.00 | $0.00 | $0.00 | $16,200.00
TS-10 | Calendario profesor |  |  | $0.00 | $0.00 | $0.00 | $16,200.00
TS-11 | Calendario alumno |  |  | $0.00 | $0.00 | $0.00 | $16,200.00
TS-16 | Dashboard profesor |  |  | $0.00 | $0.00 | $0.00 | $16,200.00
TS-17 | Dashboard alumno |  |  | $0.00 | $0.00 | $0.00 | $16,200.00
TS-12 | Calificar alumnos |  |  | $0.00 | $0.00 | $0.00 | $16,200.00
TS-18 | Pagina promocional |  |  | $0.00 | $0.00 | $0.00 | $16,200.00
TS-20 | Login redes sociales |  |  | $0.00 | $0.00 | $0.00 | $16,200.00
TS-21 | Compartir redes sociales |  |  | $0.00 | $0.00 | $0.00 | $16,200.00
TS-13 | Servicio de recomendaciones |  |  | $0.00 | $0.00 | $0.00 | $16,200.00
TS-14 | Servicio de mensajeria |  |  | $0.00 | $0.00 | $0.00 | $16,200.00
TS-15 | Reaccionar al termino de periodo de prueba |  |  | $0.00 | $0.00 | $0.00 | $16,200.00
|  | 288 | 18
$/hora.par
[8 empty] | Developers: | 50
[8 empty] | Managers: | 100